## Data
S/No | Questions | Narrative | Total Response | Strongly Agree | Agree | Nuetral | Disagree | Strongly Disagree |  |  | Response Percentage Distribution
1 | Question-5 | In the course of the construction, there were scope changes in the right of way (ROW). | 15 | 5 | 8 | 1 | 1 | 0 |  |  | S/No | Questions | Question (Text) | Total Response | Strongly Agree | Agree | Nuetral | Disagree | Strongly Disagree
2 | Question-6 | There were changes in scope during pipe stringing | 15 | 6 | 7 | 0 | 2 | 0 |  |  | 1 | Question-5 | In the course of the construction, there were scope changes in the right of way (ROW). | 100% | 33.33% | 53.33% | 6.667% | 6.667% | 0% | 54
3 | Question-7 | There were changes in scope during pipe welding. | 15 | 8 | 3 | 3 | 1 | 0 |  |  | 2 | Question-6 | There were changes in scope during pipe stringing | 100% | 40% | 46.67% | 0% | 13.33% | 0% | 2
4 | Question-8 | There were changes in scope during ditching | 15 | 5 | 6 | 1 | 3 | 0 |  |  | 3 | Question-7 | There were changes in scope during pipe welding. | 100% | 53.33% | 20% | 20% | 6.667% | 0% | 3
5 | Question-9 | There were changes in scope during crossings(road, river, railway, existing facility). | 15 | 6 | 6 | 2 | 1 | 0 |  |  | 4 | Question-8 | There were changes in scope during ditching | 100% | 33.33% | 40% | 6.667% | 20% | 0% | 4
6 | Question-10 | There were changes in scope during field tie-in welding. | 15 | 3 | 5 | 5 | 2 | 0 |  |  | 5 | Question-9 | There were changes in scope during crossings(road, river, railway, existing facility). | 100% | 40% | 40% | 13.33% | 6.667% | 0% | 5
7 | Question-11 | There were changes in scope during pre-commisioning. | 15 | 3 | 7 | 3 | 2 | 0 |  |  | 6 | Question-10 | There were changes in scope during field tie-in welding. | 100% | 20% | 33.33% | 33.33% | 13.33% | 0% | 6
8 | Question-12 | There were changes in scope during commissioning. | 15 | 3 | 6 | 3 | 3 | 0 |  |  | 7 | Question-11 | There were changes in scope during pre-commisioning. | 100% | 20% | 46.67% | 20% | 13.33% | 0% | 7
9 | Question-13 | There Were change(s) in scope during the construction of the custody transfer & metering station (CTMS)) | 14 | 5 | 3 | 4 | 1 | 1 |  |  | 8 | Question-12 | There were changes in scope during commissioning. | 100% | 20% | 40% | 20% | 20% | 0% | 8
10 | Question-14 | There Were change(s) in scope during the construction of the gas treatment plant (GTP). | 15 | 6 | 4 | 3 | 2 | 0 |  |  | 9 | Question-13 | There Were change(s) in scope during the construction of the custody transfer & metering station (CTMS)) | 93.33% | 33.33% | 20% | 26.67% | 6.667% | 6.667% | 9
11 | Question-15 | There Were change(s) in scope during the construction of the Intermediate pigging station (IPS). | 15 | 5 | 5 | 3 | 1 | 1 |  |  | 10 | Question-14 | There Were change(s) in scope during the construction of the gas treatment plant (GTP). | 100% | 40% | 26.67% | 20% | 13.33% | 0% | 10
12 | Question-16 | There Were change(s) in scope during the construction of the Oben-Node. | 15 | 4 | 5 | 4 | 1 | 1 |  |  | 11 | Question-15 | There Were change(s) in scope during the construction of the Intermediate pigging station (IPS). | 100% | 33.33% | 33.33% | 20% | 6.667% | 6.667% | 11
13 | Question-17 | A scope change management methodology is being applied to this project | 15 | 3 | 8 | 2 | 2 | 0 |  |  | 12 | Question-16 | There Were change(s) in scope during the construction of the Oben-Node. | 100% | 26.67% | 33.33% | 26.67% | 6.667% | 6.667% | 12
14 | Question-18 | The scope change methodology is well formalized. | 15 | 1 | 5 | 6 | 2 | 1 |  |  | 13 | Question-17 | A scope change management methodology is being applied to this project | 100% | 20% | 53.33% | 13.33% | 13.33% | 0% | 13
15 | Question-19 | Provision for expert consultations on critical scope changes in the methodology is well implemented on the project. | 15 | 2 | 4 | 6 | 3 | 0 |  |  | 14 | Question-18 | The scope change methodology is well formalized. | 100% | 6.667% | 33.33% | 40% | 13.33% | 6.667% | 14
16 | Question-20 | The scope changes are well predicted before their occurrence | 15 | 1 | 7 | 4 | 3 | 0 |  |  | 15 | Question-19 | Provision for expert consultations on critical scope changes in the methodology is well implemented on the project. | 100% | 13.33% | 26.67% | 40% | 20% | 0% | 15
17 | Question-21 | When scope change occurs, it is promptly attended to by the change management board. | 15 | 2 | 7 | 4 | 1 | 1 |  |  | 16 | Question-20 | The scope changes are well predicted before their occurrence | 100% | 6.667% | 46.67% | 26.67% | 20% | 0% | 16
18 | Question-22 | The feedback from the change management board is always on time in this project. | 15 | 1 | 7 | 4 | 1 | 2 |  |  | 17 | Question-21 | When scope change occurs, it is promptly attended to by the change management board. | 100% | 13.33% | 46.67% | 26.67% | 6.667% | 6.667% | 17
19 | Question-23 | The scope changes impacted on the cost of construction of this project. | 15 | 8 | 7 | 0 | 0 | 0 |  |  | 18 | Question-22 | The feedback from the change management board is always on time in this project. | 100% | 6.667% | 46.67% | 26.67% | 6.667% | 13.33% | 18
20 | Question-24 | The scope changes impacted on the duration of construction of this project. | 15 | 8 | 5 | 2 | 0 | 0 |  |  | 19 | Question-23 | The scope changes impacted on the cost of construction of this project. | 100% | 53.33% | 46.67% | 0% | 0% | 0% | 19
21 | Question-25 | The scope changes impacted on the labor productivity of construction of this project. | 15 | 4 | 7 | 3 | 1 | 0 |  |  | 20 | Question-24 | The scope changes impacted on the duration of construction of this project. | 100% | 53.33% | 33.33% | 13.33% | 0% | 0% | 20
22 | Question-26 | The scope change management impacted on the cost of construction of this project. | 15 | 5 | 9 | 1 | 0 | 0 |  |  | 21 | Question-25 | The scope changes impacted on the labor productivity of construction of this project. | 100% | 26.67% | 46.67% | 20% | 6.667% | 0% | 21
23 | Question-27 | The scope change management impacted on the duration of construction of this project. | 15 | 5 | 8 | 2 | 0 | 0 |  |  | 22 | Question-26 | The scope change management impacted on the cost of construction of this project. | 100% | 33.33% | 60% | 6.667% | 0% | 0% | 22
[11 empty] | 23 | Question-27 | The scope change management impacted on the duration of construction of this project. | 100% | 33.33% | 53.33% | 13.33% | 0% | 0% | 23
Descriptive Statistics
[10 empty] | N | Range | Minimum | Maximum | Sum | Mean | Std. Deviation | Variance | Kurtosis
[10 empty] | Statistic | Statistic | Statistic | Statistic | Statistic | Statistic | Statistic | Statistic | Statistic | Std. Error
[9 empty] | Strongly Agree | 23 | 7 | 1 | 8 | 99 | 4.3 | 2.162 | 4.676 | -0.693 | 0.935
[9 empty] | Agree | 23 | 6 | 3 | 9 | 139 | 6.04 | 1.637 | 2.68 | -0.64 | 0.935
[9 empty] | Neutral | 23 | 6 | 0 | 6 | 66 | 2.87 | 1.66 | 2.755 | -0.345 | 0.935
[9 empty] | Disagree | 23 | 3 | 0 | 3 | 33 | 1.43 | 0.992 | 0.984 | -0.873 | 0.935
[9 empty] | Strongly Disagree | 23 | 2 | 0 | 2 | 7 | 0.3 | 0.559 | 0.312 | 2.415 | 0.935
[9 empty] | Valid N (listwise) | 23

## Sheet1
500000000 |  |  |  |  | 9000000
5000000 | 1% | Service | [5 empty] | 1% |  | 5000000 | 1%
| 2% | Consultancy | [5 empty] | 2% |  | 10000000 | 2%
[8 empty] | 3% |  | 15000000
[8 empty] | 28% |  | 140000000
30000000 | 6% | Capex | [5 empty] | 6% |  | 30000000 | 6%
165000000 | 33% | P/Bond | [5 empty] | 3% |  | 15000000 | 3% |  |  | trucks
300000000 | 60% | Direct Po | 25pcs |  | 33.3333 |  |  | 38.5% | 250ps | 192500000 | 38.5% | Pt Clear | 10 | 100
| 15% | po |  |  |  | 75000000 | 25% | 15.5% |  | 77500000 | 15.5% | Haulage
| 15% | Ex works |  |  | 180000000 | 75000000 | 25% | 3% |  | 15000000 | 3% | Assemb
| 3% | FAT |  |  | 80000000 | 15000000 | 5% | 100% |  | 500000000
| 6% | FOB |  | 35pcs | 8571428.5714 | 30000000 | 10% |  |  | 0
| 9% | Pclear |  |  |  | 45000000 | 15% |  |  | 3100000
| 9% | Haul & Del |  |  |  | 45000000 | 15%
| 3% | Assemblage |  |  |  | 15000000 | 5%
5.2083
[6 empty] | 3000000 | 70
90000000 | 18% |  |  |  |  | 210000000